## Sheet1
#Project 3 | OnTimeSoftware
#Team members |  | Position
1 | Khamze Sultan Bibarys | Project manager and developer
2 | Ongadin MIras | developer & tester
3 | Marat Makhashov | Project manager
4 | Zhamel Islam | Project manager
5 | Zeinollayev Yersultan | Project manager
#Project 3 | OnTimeSoftware
#Team Members | Full Name | Position
2 | Ongadin Miras | developer & tester
#Iteration | type of iteration | Deadline | Current date | total number of stories | number of planned stories(first plan) | total number of completed stories | new planning number of stories for the next iteration | Reasons for replanning | total number of passed planned tests until iteration | number of unpassed planned tests for iteration | Comments
Verification and validation 1/4 | mid | 2022-04-25 | 2022-04-11 | 8 | 1 | 2 | 1 | Incorrect operation | 5 | 0 | Checking software
Addition of new functionality in software | mid | 2022-04-30 | 2022-04-04 | 8 | 2 | 1 | 1 | - | 10 | 3 | In addition
Testing 1/4 | mid | 2022-04-29 | 2022-04-02 | 8 | 3 | 2 | 1 | System failure | 5 | 5 | -
Configuration changes of software 1/4 | fin | 2022-04-19 | 2022-04-28 | 8 | 2 | 1 | 2 | - | 7 | 10 | not yet
Debugging 2/4 | mid | 2022-04-16 | 2022-04-05 | 8 | 4 | 0 | 2 | Piece of that failure | 10 | 15 | Correcting it
Defect fixes 1/4 | fin | 2022-04-28 | 2022-04-19 | 8 | 3 | 2 | 1 | Not correctly working | 10 | 5 | not at all
Fiinal version 2/4 | fin | 2022-04-25 | 2022-04-09 | 8 | 2 | 1 | 2 | - | 5 | 0
Project# 3 | OnTimeSoftware
#Team members | Full Name | Position
5 | Zeinollayev Yersultan | Project manager & designer
#Iteration/out of | type of iteration | Deadline | Current date | total number of stories | number of planned stories(first plan)/out of__ | total number of completed stories | new planning number of stories for the next iteration | Reasons for replanning | total number of passed planned tests until iteration | number of unpassed planned tests for iteration | Comments
Iteration plan 2/4 | mid | 2022-04-25 | 2022-02-23 | 8 | 2 | 1 | 2 | - | 5 | 10
Document design 2/4 | mid | 2022-03-22 | 2022-02-28 | 8 | 2 | 1 | 1 | - | 5 | 5
Prototyping 2/4 | mid | 2022-04-22 | 2022-03-22 | 8 | 2 | 1 | 1 | - | 7 | 3
Identify and manages risks 1/4 | mid | 15.03.2022 | 01.03.2022 | 8 | 1 | 2 | 1 | - | 10 | 10
Important Features | mid | 2022-02-25 | 08.03.2022 | 8 | 2 | 2 | 1 | - | 15 | 5
Handle exceptions and problems | fin | 2022-03-25 | 2022-04-15 | 8 | 2 | 2 | 2 | - | 10 | 0
Peformance & Control 1/4 | fin | 2023-04-25 | 2023-03-25 | 8 | 2 | 1 | 2 | - | 8 | 0
Project close 2/7 | fin | 15.03.2024 | 2022-04-05 | 8 | 2 | 0 | 2 | - | 10 | 0
| Khamze Sultan Bibarys | QA engineer and developer
#Iteration/out of | type of iteration | Deadline | Current date | total number of stories | number of planned stories(first plan)/out of__ | total number of completed stories | new planning number of stories for the next iteration | Reasons for replanning | total number of passed planned tests until iteration | number of unpassed planned tests for iteration | Comments
Iteration plan 1/5 | mid | 2022-04-20 | 2022-02-23 | 8 | 1 | 1 | 1 | - | 5 | 0
Document design 1/5 | mid | 2022-03-25 | 2022-02-28 | 8 | 2 | 1 | 1 | wrong document desing | 5 | 5
Prototyping 1/5 | mid | 2022-04-23 | 2022-03-22 | 8 | 2 | 1 | 1 | - | 7 | 3
Identify and manages risks 1/4 | mid | 2022-03-18 | 01.03.2022 | 8 | 3 | 1 | 1 | - | 10 | 10
Important Features | mid | 2022-02-26 | 08.03.2022 | 8 | 3 | 2 | 2 | not passed QA test | 15 | 5
Handle exceptions and problems | fin | 2022-03-27 | 2022-04-15 | 8 | 4 | 2 | 2 | not passed unit test | 10 | 0
Peformance & Control 1/5 | fin | 2023-04-29 | 2023-03-25 | 8 | 3 | 1 | 2 | - | 8 | 0
Project end | fin | 15.03.2024 | 2022-04-05 | 8 | 2 | 0 | 2 | some bugs | 10 | 0
3 | Zhamel Islam | Project manager
#Iteration/out of | type of iteration | Deadline | Current date | total number of stories | number of planned stories(first plan)/out of__ | total number of completed stories | new planning number of stories for the next iteration | Reasons for replanning | total number of passed planned tests until iteration | number of unpassed planned tests for iteration | Comments
Iteration plan 3/5 | mid | 2022-04-28 | 2022-02-23 | 8 | 1 | 1 | 1 | - | 5 | 0
Document design 1/5 | mid | 2022-03-25 | 2022-02-28 | 8 | 2 | 1 | 1 | wrong document desing | 5 | 5
Prototyping 1/5 | mid | 2022-04-23 | 2022-03-22 | 8 | 2 | 1 | 1 | - | 7 | 3
Identify and manages risks 1/4 | mid | 2022-03-18 | 01.03.2022 | 8 | 3 | 1 | 1 | - | 10 | 10
Important Features | mid | 2022-02-26 | 08.03.2022 | 8 | 3 | 2 | 2 | not passed QA test | 15 | 5
Handle exceptions and problems | fin | 2022-03-27 | 2022-04-15 | 8 | 4 | 2 | 2 | not passed unit test | 10 | 0
Peformance & Control 1/5 | fin | 2023-04-29 | 2023-03-25 | 8 | 3 | 1 | 2 | - | 8 | 0
Project end | fin | 15.03.2024 | 2022-04-05 | 8 | 2 | 0 | 2 | some bugs | 10 | 0
| Marat Makhashov | Project manager
#Iteration/out of | type of iteration | Deadline | Current date | total number of stories | number of planned stories(first plan)/out of__ | total number of completed stories | new planning number of stories for the next iteration | Reasons for replanning | total number of passed planned tests until iteration | number of unpassed planned tests for iteration | Comments
Iteration plan 3/5 | mid | 2022-04-28 | 2022-02-23 | 8 | 1 | 1 | 1 | - | 5 | 0
Document design 1/5 | mid | 2022-03-25 | 2022-02-28 | 8 | 2 | 1 | 1 | wrong document desing | 5 | 5
Prototyping 1/5 | mid | 2022-04-23 | 2022-03-22 | 8 | 2 | 1 | 1 | - | 7 | 3
Identify and manages risks 1/4 | mid | 2022-03-18 | 01.03.2022 | 8 | 3 | 1 | 1 | - | 10 | 10
Important Features | mid | 2022-02-26 | 08.03.2022 | 8 | 3 | 2 | 2 | not passed QA test | 15 | 5
Handle exceptions and problems | fin | 2022-03-27 | 2022-04-15 | 8 | 4 | 2 | 2 | not passed unit test | 10 | 0
Peformance & Control 1/5 | fin | 2023-04-29 | 2023-03-25 | 8 | 3 | 1 | 2 | - | 8 | 0
Project end | fin | 15.03.2024 | 2022-04-05 | 8 | 2 | 0 | 2 | some bugs | 10 | 0